## excel (5)
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Juan Pablo Ospino Solano
Start Date | abr 16, 2017 03:51:20 PM
Completion Date | abr 18, 2017 10:46:03 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 16.3 | 6.53 | 26.6
Planned Time | 0.032639 |  | 1899-12-31 02:47
Actual Tiempo |  | 0.10208 | 1899-12-31 11:34
CPI (Cost-Performance Index) |  |  | 0.75
% Reuse | 88.3% | 85.8% | 14%
% New Reusable | 0% | 0% | 6.14%
Test Defects/KLOC or equivalent | 1.08 | 0 | 1.06
Total Defects/KLOC or equivalent | 19.4 | 62.5 | 20.1
Yield % | 83.3% | 100% | 84.2%
Code Review Rate | 624 | 480 | 1050
% Appraisal COQ | 4.28% | 4.76% | 4.31%
% Failure COQ | 4.63% | 10.9% | 5.06%
COQ A/F Ratio | 0.92 | 0.44 | 0.85
PQI | 0 | 0.02 | 0.01
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 12.8 | 16 | 945
Reused (R) | 97 | 97 | 108
Added and Modified (A+M) | 12.8 | 16 | 945
Total Size (T) | 110 | 113 | 769
Total New Reusable | 0 | 0 | 58
Estimated Proxy Size (E) | 11.3 | 1 | 414
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.0048611 | 0.017361 | 0.23264 | 15.7%
DiseÃ±o | 0.0013889 | 0.039583 | 0.1125 | 7.59%
RevisiÃ³n de DiseÃ±o | 0.00069444 | 0.0034722 | 0.026389 | 1.78%
CodificaciÃ³n | 0.020139 | 0.020833 | 0.88403 | 59.7%
RevisiÃ³n de CodificaciÃ³n | 0.00069444 | 0.0013889 | 0.0375 | 2.53%
CompilaciÃ³n | 0.00069444 | 0.00069444 | 0.022222 | 1.5%
Pruebas | 0.00069444 | 0.010417 | 0.052778 | 3.56%
Postmortem | 0.0027778 | 0.0083333 | 0.11389 | 7.69%
Total | 0.032639 | 0.10208 | 1899-12-31 11:34
Total Time UPI (70%) | 0.26319
Total Time LPI (70%) | 0
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.08 | 0 | 6 | 31.6%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.17 | 1 | 13 | 68.4%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 0.25 | 1 | 19
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.01 | 0 | 1 | 5.26%
CodificaciÃ³n | 0.12 | 0 | 9 | 47.4%
RevisiÃ³n de CodificaciÃ³n | 0.07 | 1 | 6 | 31.6%
CompilaciÃ³n | 0.03 | 0 | 2 | 10.5%
Pruebas | 0.01 | 0 | 1 | 5.26%
Total | 0.25 | 1 | 19
After Development | 0 | 0 | 6
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.06 | 0 | 1.58
Defects/Hour - Code Review | 3.36 | 30 | 6.67
Defects/Hour - Compile | 2.26 | 0 | 3.75
Defects/Hour - Test | 0.57 | 0 | 0.79
DRL (DLDR/UT) | 1.85 | 0 | 2
DRL (Code Review/UT) | 5.87 | 38 | 8.44
DRL (Compile/UT) | 3.94 | 0 | 4.75
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:46 PM el 18/04/2017